EVOLUTION MEDIA

Campaign Plan

“Go Live” — 4-Week Lead Generation Sprint

Worldwide — Bootstrap Budget — April 2026

Objective

Secure the first 5 paying clients for the €499 standard package

Contents

# 1. Campaign Overview

| Field | Detail |
| --- | --- |
| Campaign Name | “Go Live” |
| Tagline | Your business online. In days. For €499. |
| Campaign Type | Lead generation (direct response) |
| Duration | 4 weeks (28 days) |
| Geography | Worldwide — English-speaking markets (IE, UK, US, AU, CA prioritised) |
| Budget | Bootstrap: up to €200/month paid (€100 ad spend + €100 boosts) |
| Channels | Organic social, direct outreach, community, small paid boosts |
| Primary Goal | Secure 5 paying clients (€50 deposit each) within 28 days |
| Secondary Goal 1 | Reach 500 organic impressions per week across Instagram + LinkedIn |
| Secondary Goal 2 | Build an email subscriber base of 50+ |
| Secondary Goal 3 | Drive 200+ unique visitors to evomedia.site |

# 2. Target Audience

## 2.1 Primary Audience — The Websiteless Business Owner

A sole trader, tradesperson, or small business owner who has been operating without a proper website — relying on Facebook, word of mouth, or a free builder they set up years ago. They know they need something better but assume it’s expensive and time-consuming.

| Attribute | Description |
| --- | --- |
| Role | Owner / Founder / Sole Trader |
| Business types | Tradespeople, cafés & restaurants, beauty & wellness, retail, coaches, consultants, photographers, freelancers |
| Company size | 1–10 employees |
| Age range | 25–55 |
| Tech comfort | Moderate — comfortable on social, scared of code |
| Pain point | No website or embarrassing outdated site; losing credibility and leads to competitors who look more professional online |
| Motivation | Look legit, get found on Google, stop losing customers at the first impression |
| Objection #1 | “It’s too expensive” — counter: €499 fixed, no hidden fees |
| Objection #2 | “It takes too long” — counter: live in 3–7 days |
| Objection #3 | “I don’t know what I need” — counter: we guide you, no jargon |
| Where they are | Instagram, Facebook groups, Google search, LinkedIn (B2B segment), TikTok |
| Buying stage | Awareness → Consideration (most don’t know a fast affordable option exists) |

## 2.2 Secondary Audience — The Rebrand / Upgrade Buyer

A business that has a website but it’s slow, outdated, or built on a platform they’ve outgrown (old WordPress, Wix, Squarespace). They’re actively looking to upgrade and open to switching.

| Attribute | Description |
| --- | --- |
| Pain point | Current site is slow, ugly on mobile, or they’ve lost control of it |
| Motivation | Fresh, fast, professional — and they want to own it properly this time |
| Buying stage | Consideration → Decision (they’ve already decided to upgrade; choosing who) |
| Where they are | Google search (“web design Ireland”, “cheap website redesign”), LinkedIn, Reddit r/Entrepreneur |

# 3. Key Messages

## 3.1 Core Campaign Message

“Your business deserves a proper website. We build it in days, for €499 — custom designed, mobile-ready, and yours to keep.”

## 3.2 Message Hierarchy

| Layer | Message | Addresses |
| --- | --- | --- |
| 1. Why care? | Every day without a proper website is a day you’re losing potential customers to competitors who look more professional. | Pain point: credibility gap |
| 2. What’s the solution? | Evolution Media builds custom one-page websites in 3–7 days, starting at €499 — no templates, no hidden costs. | Solution positioning |
| 3. Why us? | No template designs. No lock-in. No surprise invoices. You own everything on launch day. | Differentiation from Wix/agencies |
| 4. What to do? | Pay a €50 deposit to get started. Site goes live in days. | Low-friction CTA |

## 3.3 Message Variations by Channel

| Channel | Hook | Tone |
| --- | --- | --- |
| Instagram / TikTok | “We built this site in 4 days. Here’s how.” / before-and-after visuals | Visual-first, punchy, proof-led |
| LinkedIn | “Small businesses are losing clients every day because their website looks like 2014.” | Thought leadership, slightly provocative |
| Facebook groups | “Hey, I’m a web developer based in Ireland — just wanted to share something that might help...” | Warm, community, value-first |
| Direct outreach | “I noticed your business doesn’t have a website yet. I build them in a week for €499.” | Direct, specific, respectful |
| Google / SEO | “Custom web design from €499 — live in days” | Search-intent matched, clear |
| Email newsletter | “Here’s what a good one-page website needs (and what most get wrong).” | Educational, builds trust |

# 4. Channel Strategy

| Channel | Role in Campaign | Content Format | Effort | Budget |
| --- | --- | --- | --- | --- |
| Instagram (organic) | Awareness + portfolio proof | Reels (builds, before/after), carousels (tips), Stories (behind-scenes) | High | €0 |
| LinkedIn (organic) | B2B awareness + credibility | Short-form posts, thought leadership, project announcements | Medium | €0 |
| TikTok (organic) | Reach new audiences via algorithm | 30–60s build walkthroughs, ‘things I wish I knew’ tips for biz owners | Medium | €0 |
| Facebook Groups | Direct community lead gen | Value-add posts in small biz / entrepreneur / local business groups | Medium | €0 |
| Reddit | Organic reach in SMB communities | Helpful posts in r/smallbusiness, r/entrepreneur, r/webdev | Low | €0 |
| Direct outreach (DM/email) | High-conversion direct lead gen | Personalised short message to businesses without websites | High | €0 |
| Meta paid boost | Amplify best-performing organic post | Boost top organic post to ‘Small business owners’ lookalike audience | Low | €100 |
| Newsletter / email | Nurture + trust-building | 1 email per week: tip + project feature + soft CTA | Low | €0 |
| Google Business Profile | Local / branded search visibility | Complete profile, add portfolio images, request reviews | Low | €0 |
| Website (SEO) | Passive inbound over time | Clear CTA on every section, FAQ schema markup, location page | Low | €0 |

## 4.1 Channel Priority Order

Given the bootstrap budget, invest time in this order:

- 1. Direct outreach — highest conversion rate, zero cost, immediate feedback.

- 2. Instagram Reels — best organic reach potential; portfolio content is naturally shareable.

- 3. Facebook groups — targeted communities of exact buyers, low competition.

- 4. LinkedIn — reaches B2B buyers and builds professional credibility.

- 5. TikTok — highest ceiling for viral reach; lower conversion, higher awareness.

- 6. Meta paid boost — deploy in Week 3 once you know which organic content resonates.

- 7. Email newsletter — small list but highest quality; nurtures people who aren’t ready yet.

## 4.2 Direct Outreach Playbook

This is the highest-leverage channel for a brand-new business. The process:

| Step | Action | Tools |
| --- | --- | --- |
| 1 | Identify 20 businesses per day that have no website or an outdated one (check Google Maps in target towns/industries) | Google Maps, Google search |
| 2 | Find the owner’s name from Google, Facebook, or LinkedIn | LinkedIn, Facebook |
| 3 | Send a short, personalised message via Instagram DM, Facebook message, or email | Instagram, Facebook, email |
| 4 | Follow up once after 3 days if no reply — one follow-up only | Same channel |
| 5 | Track responses in a simple spreadsheet: Name ¦ Business ¦ Channel ¦ Status ¦ Date | Google Sheets or Notion |

Outreach message template (adapt per business):

Hi [Name], I noticed [Business Name] doesn’t have a website yet — or the current one might be due a refresh. I’m a web designer based in Ireland and I build custom sites in about a week, starting at €499. No templates, you own everything. Happy to chat if it’s useful. — John, Evolution Media

Target: 20 outreach messages per day = 140 per week = 560 over the campaign. A 5% response rate = 28 conversations. A 20% close rate from conversations = 5–6 clients.

# 5. Four-Week Content Calendar

## 5.1 Weekly Themes

| Week | Theme | Focus |
| --- | --- | --- |
| Week 1 | Launch & Establish | Get all channels live, publish launch content, start outreach |
| Week 2 | Proof & Portfolio | Show the work — portfolio posts, process videos, case studies |
| Week 3 | Objection Busting | Address price, time, and complexity concerns with content |
| Week 4 | Convert & Close | Strong CTAs, urgency, follow-ups, first testimonials |

## 5.2 Day-by-Day Calendar

| Day | Content Piece | Channel | Notes | Status |
| --- | --- | --- | --- | --- |
| WEEK 1 — LAUNCH & ESTABLISH |  |  |  |  |
| 1 | Profile optimisation: update all bios, links, and profile images across Instagram, LinkedIn, TikTok, Facebook | All social channels | Link to evomedia.site in all bios | To Do |
| 1 | Google Business Profile: complete listing, add portfolio photos | Google | Service area: Worldwide | To Do |
| 2 | Launch post: “Evolution Media is open for business” announcement with site preview | Instagram + LinkedIn | Link to site. Pin this post. | To Do |
| 2 | Reel: 30-second screen recording walkthrough of evomedia.site with voiceover | Instagram + TikTok | Caption: “We built this in 4 days. Here’s what’s included for €499.” | To Do |
| 3 | Start direct outreach: 20 businesses (tradespeople, cafes, beauty) | DM / Email | Use outreach template. Track in spreadsheet. | To Do |
| 3 | LinkedIn post: “Why small businesses are losing clients before they even make contact” (thought leadership) | LinkedIn | No CTA yet — awareness post only | To Do |
| 4 | Carousel: “5 things your website needs in 2026” (educational) | Instagram | Slide 5 soft CTA to Evolution Media | To Do |
| 4 | Continue outreach: 20 businesses | DM / Email | Day 2 of outreach | To Do |
| 5 | Facebook group post: introduce yourself + offer value (“3 signs your website is losing you customers”) | Facebook Groups | Post in 3–5 relevant groups. Value-first, no hard sell. | To Do |
| 5 | Email #1: Welcome / brand intro to any early subscribers | Email | Subject: “How to get your business online fast (and what it actually costs)” | To Do |
| 6 | TikTok: “Day in the life building a client website” behind-the-scenes | TikTok | Casual, authentic tone | To Do |
| 6 | Continue outreach: 20 businesses | DM / Email | Day 3 of outreach | To Do |
| 7 | Weekly review: check engagement stats, respond to all comments/DMs, adjust Week 2 plan | Internal | Note what performed best to inform Week 3 boost | To Do |
| WEEK 2 — PROOF & PORTFOLIO |  |  |  |  |
| 8 | Portfolio Reel #1: showcase a sample project with before/after or walkthrough | Instagram + TikTok | Use portfolio samples from /public/portfolio-samples/ | To Do |
| 9 | LinkedIn: “What we build and why it works” — explain the 3-step process (Brief, Build, Launch) | LinkedIn | Reinforce process transparency | To Do |
| 9 | Continue outreach: 20 businesses / day | DM / Email | Follow up with Day 1 outreach (sent Day 3) | To Do |
| 10 | Carousel: “What’s included in a €499 Evolution Media site” (feature breakdown) | Instagram | Visual breakdown of Hero / Services / About / Contact + SEO + Mobile | To Do |
| 11 | Portfolio Reel #2: second sample project | Instagram + TikTok | Different industry to Week 2 Reel #1 | To Do |
| 11 | Reddit post: “I build custom websites in under a week — AMA” or helpful post | Reddit | r/smallbusiness or r/Entrepreneur. Lead with value, no promo | To Do |
| 12 | Email #2: “See what we built this week” — portfolio feature + soft CTA | Email | Include project screenshot and link to full portfolio | To Do |
| 12 | Facebook group: share a portfolio piece with context (“Just launched this for a local business...”) | Facebook Groups | Include before/after if available | To Do |
| 13 | TikTok: “How I build a website in 4 days” — time-lapse / process breakdown | TikTok | High shareability, educational format | To Do |
| 14 | Weekly review + identify top-performing post for Week 3 paid boost | Internal | This post will receive the €100 Meta boost in Week 3 | To Do |
| WEEK 3 — OBJECTION BUSTING |  |  |  |  |
| 15 | Reel: “Is €499 cheap for a website? Here’s what you actually get.” | Instagram + TikTok | Address price objection directly. Show value. | To Do |
| 15 | €100 Meta ad boost: run best Week 2 post to ‘Small business owners’ worldwide audience | Meta Ads | Budget: €100 over 7 days. Objective: website clicks. | To Do |
| 16 | LinkedIn: “Why most agency websites take 3 months (and what we do differently)” | LinkedIn | Address time objection. Explain the workflow. | To Do |
| 16 | Continue outreach: 20 businesses / day | DM / Email | New batch + follow up Week 2 outreach | To Do |
| 17 | Carousel: “Wix vs. a custom site — what’s the real difference?” | Instagram | Fair comparison. Not disparaging. Positions Evolution Media clearly. | To Do |
| 18 | Email #3: “The 3 questions people ask before getting a website built” (FAQ format) | Email | Address: cost, time, do I need one. Ends with CTA. | To Do |
| 19 | TikTok: “Things web designers won’t tell you” (myth-busting, shareable) | TikTok | e.g., you don’t need 20 pages; you DO need mobile-first | To Do |
| 19 | Facebook group: answer web design questions / share tips (community-first) | Facebook Groups | No promo. Pure value. Builds trust and visibility. | To Do |
| 21 | Weekly review: check Meta ad performance, decide whether to extend or adjust | Internal | If CTR > 1.5%, extend with €50 more from contingency | To Do |
| WEEK 4 — CONVERT & CLOSE |  |  |  |  |
| 22 | Reel: first client success story or site launch announcement | Instagram + TikTok | If a client is live, feature them (with permission). Otherwise use a sample. | To Do |
| 22 | LinkedIn: “We’ve launched [N] sites in 4 weeks. Here’s what we learned.” | LinkedIn | Reflection post. Builds credibility. Invite enquiries. | To Do |
| 23 | Email #4: “Last chance to lock in your site this month” — direct CTA | Email | Genuine urgency (capacity limit or end of campaign period). €50 deposit CTA. | To Do |
| 23 | Follow up all unanswered outreach from Weeks 1–3 | DM / Email | Final follow-up message. Short and respectful. | To Do |
| 24 | Carousel: “How to get started with Evolution Media — 3 steps, 5 minutes” | Instagram | Remove friction. Show deposit CTA clearly. | To Do |
| 25 | TikTok: “What happens after you pay the €50 deposit?” (process explainer) | TikTok | Eliminates last-minute hesitation. Reassures on process. | To Do |
| 26 | Facebook group: final value post + soft mention that you have 2–3 spots open | Facebook Groups | Scarcity message. Authentic, not manufactured. | To Do |
| 27 | Request testimonials from any clients who went live during the campaign | Email / DM | Use their words in next campaign’s social proof content | To Do |
| 28 | Campaign debrief: compile results, document learnings, plan Campaign 2 | Internal | Use the KPI tracker to assess against targets | To Do |

# 6. Content Assets Required

| Asset | Type | Description | Priority | Due |
| --- | --- | --- | --- | --- |
| Profile images & bios | Setup | Consistent profile photos, bios, and links across all channels | Must-have | Day 1 |
| Site walkthrough Reel | Video (30s) | Screen recording of evomedia.site with voiceover explaining what’s included | Must-have | Day 2 |
| Launch announcement post | Image + copy | Branded graphic with “Evolution Media is open” copy | Must-have | Day 2 |
| Outreach spreadsheet | Document | Tracking sheet: Business ¦ Name ¦ Channel ¦ Status ¦ Date contacted | Must-have | Day 3 |
| Outreach message templates | Copy | 3–5 personalised variations for different business types | Must-have | Day 3 |
| “5 things your website needs” carousel | Carousel (5 slides) | Educational Instagram carousel with soft CTA on final slide | Must-have | Day 4 |
| Portfolio Reel #1 & #2 | Video (30–60s) | Screen walkthrough or mock build of 2 different sample sites | Must-have | Day 8 + 11 |
| “What’s included” carousel | Carousel (6 slides) | Visual breakdown of €499 package features | Must-have | Day 10 |
| Email welcome sequence (4 emails) | Email copy | 4 weekly emails: intro, portfolio, FAQ/objections, conversion CTA | Must-have | Day 1 (drafted) |
| LinkedIn thought leadership posts (4) | Copy | One per week, each covering a different angle | Must-have | Weekly |
| Meta ad creative | Image or short video | Best-performing organic post, adapted for paid: clear value prop, CTA | Must-have | Day 14 |
| Wix vs. custom comparison carousel | Carousel | Fair, factual comparison positioning Evolution Media clearly | Should-have | Day 17 |
| FAQ Reel (“Is €499 cheap?”) | Video (30s) | Address price objection directly. Confident, not defensive. | Should-have | Day 15 |
| Client launch post template | Image + copy | Celebratory post for when a client site goes live | Should-have | Week 4 |
| Testimonial request message | Copy | Short message asking happy clients for a quote/screenshot | Should-have | Day 27 |
| Google Business Profile images | Photos | Screenshots of portfolio sites, studio/work environment | Nice-to-have | Day 1 |
| TikTok series: ‘Things web designers won’t tell you’ | Video series | 3-part myth-busting series for shareability | Nice-to-have | Week 3 |

# 7. Success Metrics & KPIs

## 7.1 Primary KPI

5 paying clients secured (€50 deposit each = €250 total deposits, €2,495 full value) within 28 days.

## 7.2 KPI Dashboard

| Metric | Target | How to Track | Cadence |
| --- | --- | --- | --- |
| Paying clients (deposits received) | 5 | Stripe / payment dashboard | Daily (Week 4) |
| Outreach messages sent | 560 total (140/week) | Outreach spreadsheet | Daily |
| Outreach response rate | >5% | Outreach spreadsheet | Weekly |
| Sales conversations opened | >25 | Outreach spreadsheet | Weekly |
| Instagram profile visits | >500 total | Instagram Insights | Weekly |
| Instagram Reel views | >2,000 total | Instagram Insights | Per post |
| LinkedIn impressions | >1,000 total | LinkedIn Analytics | Weekly |
| TikTok views | >5,000 total | TikTok Analytics | Weekly |
| Website unique visitors | >200 | Vercel Analytics / GA4 | Weekly |
| Email subscribers | >50 | Email platform | Weekly |
| Email open rate | >40% | Email platform | Per send |
| Meta ad CTR | >1.5% | Meta Ads Manager | Daily (Week 3) |
| Meta ad cost per click | <€0.50 | Meta Ads Manager | Daily (Week 3) |

## 7.3 Reporting Cadence

- Daily: Check outreach responses and reply within 2 hours. Monitor any paid ad spend.

- Weekly (Monday): Review previous week’s social stats, email performance, and outreach numbers. Update the KPI tracker. Adjust content plan if needed.

- End of campaign (Day 28): Full debrief — compare actuals vs. targets, document what worked, plan Campaign 2.

# 8. Budget Allocation

| Item | Cost | When | Notes |
| --- | --- | --- | --- |
| Meta ad boost (best organic post) | €100 | Week 3, Days 15–21 | 7-day campaign, worldwide small biz owners, website clicks objective |
| Canva Pro (if not already subscribed) | €0–13 | Month 1 | For carousel and image creation. Free tier may be sufficient. |
| Email platform (e.g., Mailchimp free tier) | €0 | Ongoing | Free up to 500 subscribers |
| Buffer / Later free tier for scheduling | €0 | Ongoing | Schedule posts in advance to save daily time |
| Contingency (extend Meta boost if CTR >1.5%) | €50–100 | Week 3–4 | Only deploy if paid is clearly working |
| Total | €100–213 | — | Well within €200 bootstrap budget |

Every euro spent outside organic channels should be unlocked by performance signals, not a fixed plan. If organic outreach is already generating client conversations, the €100 ad budget can be held in reserve for Campaign 2.

# 9. Risks & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Outreach ignored or marked as spam | Medium | High | Keep messages short, personal, and value-led. Never bulk-send. Cap at 20/day. If DM response rate < 2% by Day 7, test email outreach instead. |
| No organic social traction in Week 1–2 | Medium | Medium | Prioritise Reels and TikTok (algorithm-friendly). Post consistently. Engage with comments. Don’t chase vanity metrics — outreach is the primary channel. |
| Meta ad spend wasted on low-intent traffic | Low–Medium | Medium | Only boost a post already proven to perform organically. Set a €20/day cap. Review CTR after 48 hours; pause if below 1%. |
| Client capacity overload (>5 enquiries at once) | Low | Medium | Good problem. Use the contact form to qualify and stage intake. Clearly set expectations on timeline in all comms. |
| No testimonials / social proof available in Week 4 | Medium | Medium | Use portfolio samples and the site itself as proof. Frame sample sites as ‘what a €499 site looks like’ rather than client work. |

# 10. Next Steps

## Before Day 1 (Pre-launch checklist)

- Confirm evomedia.site is live, all sections complete, and the €50 deposit payment link works.

- Set up Instagram, LinkedIn, TikTok, and Facebook pages if not already done. Optimise all bios with link to site.

- Create and test the contact form. Set up a 24-hour auto-reply.

- Set up a free Mailchimp (or equivalent) account and create the welcome email.

- Build the outreach tracking spreadsheet.

- Draft the 5 outreach message templates.

- Create the launch graphic (Canva) and write the Day 2 launch post caption.

- Record the 30-second site walkthrough Reel.

## Campaign 2 Preview

Once Campaign 1 closes, the recommended focus for Campaign 2 is:

- SEO content push — publish 4 blog posts targeting ‘web design [city/country]’ and ‘cheap website for small business’ keywords.

- Testimonial-led content — use real client quotes and results from Campaign 1.

- Referral programme — offer existing clients €50 credit or a discount for each referral who converts.

- Increase Meta budget to €300–500/month with retargeting enabled.

Evolution Media — “Go Live” Campaign Plan v1.0 — April 2026

evomedia.site